## Workplan
Flood Risk Mapping DaNang, Vietnam
Workplan
| Legend: | M - Client Meeting; W - In-person Stakeholder Engagement; dd - Draft Submission; R - Client review; Dx - Final Deliverable Submission
| Project Week | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Activity Week commencing | 2024-05-01 | 2024-05-08 | 2024-05-15 | 2024-05-22 | 2024-05-29 | 2024-06-05 | 2024-06-12 | 2024-06-19 | 2024-06-26 | 2024-07-03 | 2024-07-10 | 2024-07-17 | 2024-07-24 | 2024-07-31 | 2024-08-07 | 2024-08-14 | 2024-08-21 | 2024-08-28 | 2024-09-04 | 2024-09-11 | 2024-09-18 | 2024-09-25 | 2024-10-02 | 2024-10-09 | 2024-10-16 | 2024-10-23 | 2024-10-30 | 2024-11-06 | 2024-11-13 | 2024-11-20 | 2024-11-27
PROJECT ADMINISTRATION
Contract signature
Team Mobilisation
Progress Update Meetings with the Client | bar: 2024-06-05; 2024-07-03; 2024-07-31; 2024-08-28; 2024-09-25; 2024-10-23; 2024-11-20
Progress Update Meeting with Beneficiary (DaNang Municipality) | bar: 2024-06-12; 2024-07-10; 2024-08-07; 2024-09-04; 2024-10-02; 2024-10-30; 2024-11-27
Close-out Meeting
Task 1: Project Inception | bar: 2024-05-08 to 2024-06-19
1.1 | Inception Meeting with Local Municipality and Stakeholders | bar: 2024-05-22
1.2 | Review of existing Flood Risk Assessment in DaNang | bar: 2024-05-08 to 2024-05-22
1.2 | Deliverable 1: Inception Report (Confirm Delivery Approach) | 2024-06-05: dd; 2024-06-12: R; 2024-06-19: D1
Task 2: Flood Risk Mapping | bar: 2024-06-26 to 2024-09-25
2.1 | Urban Expansion Analysis | bar: 2024-06-26 to 2024-08-07
2.2 | Flood Risk Analysis | bar: 2024-07-24 to 2024-09-04
2.3 | Deliverable 2: Flood Risk Application / Dashboard | 2024-09-11: dd; 2024-09-18: R; 2024-09-25: D2
Task 3: Policy Recommendations | bar: 2024-10-02 to 2024-11-13
3.1 | Workshop - Present Findings & Discuss Recommendations | bar: 2024-10-02 to 2024-10-09
3.2 | Develop Policy Recommendations | bar: 2024-10-02 to 2024-10-23
3.3 | Deliverable 3: Final Report for Publication | 2024-10-30: dd; 2024-11-06: R; 2024-11-13: D3
Task 4: Capacity Building
3.1 | Capacity Building Manual | 2024-06-19: dd; 2024-06-26: R; 2024-07-03: D4
4.1 | Capacity Building 1 - Flood risk Assessment: Approach/Methods | bar: 2024-06-26 to 2024-07-10
4.2 | Capacity Building 2 - Data Risk Assessment: Interpreating Findings | bar: 2024-09-11 to 2024-09-25
4.3 | Capacity Building 2 - Managing Data | bar: 2024-11-13 to 2024-11-27

## Costs
Position | Number of Days | Daily Fees | Total
Team Leader | 30 | 1200 | 36000 | a day a week
Project Manager | 30 | 700 | 21000 | a day a week
Local Project Coordiantor | 40 | 400 | 16000 | more than a day a week
Senior Flood Risk Expert | 15 | 1200 | 18000 | Guidance and Review
Flood Risk Expert | 40 | 700 | 28000 | Does the work
Senior Remote Sensing Analyst | 15 | 1200 | 18000 | Guidance and Review
Remote Sensing Analysts | 40 | 600 | 24000 | Does the work
Data visualisation Expert | 30 | 600 | 18000 | Makes findings look good
Urban Planner | 3 | 800 | 2400 | Recommendations
Urban Infrastructure Expert | 3 | 800 | 2400 | Recommendations
Capacity Development Expert | 20 | 500 | 10000 | 3 Cap Dev Workshops plus organisating
Total Labour | 232 |  | 193800
Total Expenses |  |  | 60000
Total Project Costs |  |  | 253800

## Sheet1
D1
D2
D3
D4
D5